## Sheet1
|  |  |  | Semester A | [11 empty] | Semester B | [11 empty] | Semester C
Phase | Task | Due Date | Status | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27
Research Phase | Project Definition
| Background Research & Context | 2021-07-02 | Completed | bar: Semester A W1 to Semester A W2
| Aims & Objectives | 2021-09-06 | Completed | bar: Semester A W1 to Semester A W2
| Problem Definition Submission | 2021-10-18 | Completed | bar: Semester A W3 to Semester A W4
Research Methodology
| Literature Review | 2021-10-25 | Completed | bar: Semester A W1 to Semester A W8
| Primary Research | 2021-10-28 | Completed | bar: Semester A W5 to Semester A W8
| Testing Criteria Research | 2021-11-03 | Completed | bar: Semester A W4 to Semester A W8
| Technology implementation research | 2021-11-05 | Completed | bar: Semester A W5 to Semester A W7
| Machine learning implementation research | 2021-11-17 | Started | bar: Semester A W8 to Semester A W12
Interim Presentation
| Interim Report | 2021-11-29 | Completed | bar: Semester A W7 to Semester A W10
| Progress Slides | 2021-12-06 | Completed | bar: Semester A W9 to Semester A W11
| Progress Presentation | 2021-12-13 | Started | bar: Semester A W12
Machine Learning Phase | Design & Development
| Environment setup | 2022-01-31 | Started | bar: Semester A W9 to Semester A W10
| Data gathering implementation | 2022-02-07 | Not Started | bar: Semester A W9 to Semester A W10
| Implementation of algorithm | 2022-03-22 | Started | bar: Semester A W10 to Semester B W21
| train algorithm | 2022-03-27 | Not Started | bar: Semester B W18 to Semester B W22
Application Phase | design user interface | 2022-03-25 | Completed | bar: Semester A W7 to Semester A W10
| implement design | 2022-04-06 | Not Started | bar: Semester B W19 to Semester B W21
| Integrate algorithm with UI | 2022-04-06 | Not Started | bar: Semester B W22
Finalisation Phase | Report
| Draft Report | 2022-03-21 | Not Started | bar: Semester B W21
Testing
| Write tests for python backend | 2022-04-21 | Not Started | bar: Semester B W21 to Semester B W24
| Write tests for javascript frontend | 2022-04-22 | Not Started | bar: Semester B W22 to Semester B W24
| Test & document for backend | 2022-04-30 | Not Started | bar: Semester B W23 to Semester B W24
| Test & document for frontend | 2022-04-30 | Not Started | bar: Semester B W23 to Semester B W24
Conclusion
| Project Video Submission | 2022-05-06 | Not Started | bar: Semester B W22 to Semester C W25
| Final Report Submission | 2022-05-04 | Not Started | bar: Semester B W21 to Semester C W27
| Viva | 09 to 20 May 22 | Not Started | bar: Semester C W26 to Semester C W27